## P8 2014- P1 2015
|  |  | WBL-IE Schedule for activities | Activity plan vers 0.2
|  | Agreed short term plan; phases 1.-12. |  | Updated 24.09.2014
The red number means the First draft for project partners to comment, Green number is Final agreed version for use. Ready.
Green rows show for the partners the time between dates reserved for executing feedback creation, commenting, meeting etc.
The time the task manager needs for creating the first draft not included in GANTT.
The color of the phase numberbox show the status of the agreed short term activity. RED NOT READY, YELLOW ACTIVITY ONGOING, GREEN READY
Each Task/WP manager takes care that all partners has commented and agreed. Update of the status to be informed to PC, POM and PQM + possible daviations.
Ph- | Responsible |  | Activity Headline and sub tasks |  | August |  | September |  |  |  | October |  |  | November |  |  |  | December |  |  |  | January 2015
ase
1. | WP6 | Iikka/Elina | Short term activity plan |  |  | 29. |  |  | 25.
2. | WP6 | Iikka/Elina | Update the project manual | [6 empty] | 30 | ?
3. | ? |  | Setting up Website and ADAM portal | (Drop box ready 26) | [5 empty] | 30 | ?
4. | WP2 | Ton,Alle | Specification of WBL-IE frame for the base | [5 empty] | 22. | 30. | ?
| WP3 | Bente | of the WBL-IE project and for approaching companies
5. | WP7 | Dieter, Mag- | Development of information package | [6 empty] | 30. | ?
| WP5 | nus/Ove | to approach companies (based on activity 4.)
6. | WP1 | Donal | Specification and Template to be used in approaching
| WP6 | WP6 team | companies first time for evaluating the feedback | [5 empty] | 26. |  | ?
7. | WP6 | Iikka/Elina | Development of working procedure for |  |  |  |  | 15. |  |  | ?
| WP1 | Donal | Advisory Board (way of working expectations etc.)
8. | WP1 | Donal | Plan the approaching of AB and materials to be sent | [6 empty] | ?
| WP6 | Iikka/Elina
9. | WP7 | Dieter | Dissemination, exploitation and awareness building
|  | Donal | (First draft marketing material and ) List of potential | [6 empty] | 30. |  | ?
|  | All | dissemination channels (all sent own ideas to Donal)
10. | WP1 | Donal | Evaluation/Feedback documents based on project objektives | [5 empty] | 24.
| WP6 | Iikka/Elina | Creation of document for use with Project Manual | [6 empty] | 30. |  | ?
and quality criteria
11. | WP6 | Iikka/Elina | Creation of evaluation process description for WBL-IE | [6 empty] | 30. |  | ?
| WP1 | Donal | project and its outputs
12. | ALL |  | Pilot. All partners approach companies to test the | [8 empty] | 8. contacting |  |  | 15.
interest of the Frame and participation to pilot
13. | WP5 | Magnus | Feedback collection and summary of the | [12 empty] | 18.
|  | Ove | pilot approach to companies
14. | WP5 | Magnus | Fixing possible deviations in materials created so far | [12 empty] | 21. |  | 1.
| /All | Ove | the frame, it`s content, information package etc.
15. | WP2 | Ton,Alle | Description of the approach to identify the SME | [9 empty] | 15. |  |  |  |  | 5.
| WP3 | Bente | training needs in the organizations and individuals
16. | WP2 | Ton,Alle | Specification of tools to be used to measure | [9 empty] | 15. |  |  |  |  | 5.
| WP3 | Bente | the skills (needs)for individuals in SME
17. | WP3 |  | Specifications of tools to be used when describing | [9 empty] | 15. |  |  |  |  | 5.
work tasks and learning outcomes in the use of WBL-IE frame
18. |  |  | Specifying the process for matching results of individual | [13 empty] | 28. |  |  | 22.
| WP2 | Ton,Alle | skill needs in company to the IESE and EQF frameworks
including materials to be used (ensuring quality)
19. | WP3 | Bente | Creation of the training materials for training the | [19 empty] | 9.
facilitators
20. | WP6 |  | Feedback templates to be used in pilot training for partners | [17 empty] | 29. |  |  | 20.
for evaluating quality of the training .
Templates to be used in pilots 2015
21. | WP6 |  | Creation of Quality criteria for the outputs of phases | [15 empty] | 19. |  |  | 2.
11.-12. for the use in pilots 2015
22. | WP3 |  | Execution of the faciltator training (for partners) | [21 empty] | 28.
23. | WP6 |  | Creation / crosscheck of all needed quality criteria
|  |  | to be used in facilitator trainings and WBL-IE activity | [18 empty] | 1.
in pilots 2015. Templates to be used.Quality quideline
24. | WP5 |  | Business Plan- first draft, how the project will be | [14 empty] | 1.
sustained post implementation
25. | WP1 |  | Check that all needed materials, descriptions,
| ALL |  | instructions and procedures to execute the pilots exist.
26. | WP6 |  | Creation of Quality criteria and validation process
|  |  | for matching stated objectives of the WBL-project | [7 empty] | 3. |  |  | 1.
to activity plan for medium and long term activities
in the project --> to be used for checking deviations
27. | WP3 |  | Quality criteria for testing suitable facilitators
| WP6 |  | arrangements and execution of training and
evaluating (testing) the success of the training and
facilitators learning
28. | WP1 |  | Define process for SME`S to identify future | [14 empty] | 1.
skills needs and avoid skills mismatches
29. |  |  | Field test process description
30. |  |  | Creation of procedure for evaluating the pilots
31. |  |  | Describing the procedure for summarizing and fixing
the materials, descrptions etc. For final reslults from
WBL-IE project and end reporting
30. | WP5 |  | Rollout plan
TO BE CONTINUED in sheet P1-P12 2015

## P1 - P12 2015
P1 2015