Update report for the IEA President

Presentation at Aachen, 28-29 March, 2025

Prepared by Andrew Thatcher, President

The President represents the IEA, chairs the Council and Executive Committee meetings, forms new ad hoc Committees and restructures existing executive committees, appoints Chairs to Committees, and oversees the work of Committees.

Summary plan for 2024-2027 term

| Project / initiative | How does this create value-added? | How does it align with IEA strategies policies | What needs will be met | Goals associated | Milestones (Outline to measure progress) | Current status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Supporting the growth and sustainability of HF/E through developing and supporting the next generation HF/E people | Ensure successive pipeline of researchers, practitioners, and future leaders | Engage stakeholders Contribute to Science, Technology, and Practice | Succession planning | Production of career videos. | Project initiation, second half of 2025. Video collection 2025 and 2026 Project completion first half of 2027 | Project in development |
| 2. Reflecting on the Strategy for the Future of HF/E (Dul et al., 2012) – what has worked, what has not worked, what must still be done | Provide direction for IEA | Contribute to Science, Technology, and Practice Maintain a Future Focus for HF/E | Future focus | Production of paper Revised strategy development | Development Workshops (through 2025) Paper submitted (early 2026) Paper accepted (end 2026) Strategy development (through 2026) | Project launched 4 March 2025 |
| 3. Strengthening bonds with key international organisations where we already have strong bonds: ISO, ILO, WHO | Building capacity to support HF/E internationally | Contribute to Science, Technology, and Practice Strengthen Relationships with External Partners | Relationship building | Ongoing | Regular meetings with international organisations. Joint project initiation. | Meet with ILO and WHO in March 2025 Meet with ISO in April 2025 AGS Chair appointed 5 March 2025 New MoUs negotiated (end 2025to end 2026) |

Supporting the growth and sustainability of HF/E through developing and supporting the next generation HF/E people

- What stakeholders (groups) are involved, in what roles

- Succession planning will be done in conjunction with the Professional Standards and Education Standing Committee (PSE), the International Development Standing Committee (ID), and the Development and Promotions Standing Committee (DP)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by PSE, ID, and DP | Influencer |
| Project leader/s | - Direction to the video collections | Experts and influencers |
| Experts | - Provide video content | Experts |

- Benefits to stakeholders

- Supportive material to attract and retain young people to the HF/E discipline

- Video content to share with Federated Society stakeholders

- Video content to share with other IEA stakeholders

- Table of activities and resources required

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Project not yet initiated | N/A | N/A | N/A |

- Outcomes to date (list)

Signed renewal of Tsinghua and Kingfar Awards

Ambassador visit: Shenzhen 2024 (Keynote address at CES conference and handing out awards for student papers).

Ambassador visit: Zagreb 2024 (Keynote address at CSE conference)

Ambassador visit: Subraya 2024 (Keynote address at PEI conference – online)

Ambassador visit: SustainX 2025 (Keynote address at HESP student award conference – online)

Ambassador visit: Douliu 2025 (Keynote address at EST conference and handing out awards for student papers)

- Future Activites (list)

Assign project leader/s (Andrew Todd willing to lead)

Ambassador visit: Mexicali 2025 (Keynote address at SEMAC conference)

Ambassador visit: Aachen 2025 (Keynote address at GfA Spring congress)

Reflecting on the Strategy for the Future of HF/E (Dul et al., 2012) – what has worked, what has not worked, what must still be done

- What stakeholders (groups) are involved, in what roles

- This future planning activity will be done specifically in conjunction with the Science, Technology, and Practice Standing Committee (STP)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by STP and President | Influencer |
| Project leader/s | - Development of analysis and content | Experts and influencers |
| Experts | - Development of paper and strategy workshops | Experts |

- Benefits to stakeholders

- Evaluation of Dul et al. (2012) strategy – successes, failures, progress

- Development of new/refinement of existing strategy based on evaluation

- Table of activities and resources required

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Project initiation on 4 March 2025 | HFESA, CIEHF, HFES, ESSA, CES, GfA | 2 hours + 10 hours planning | None yet |

- Outcomes to date (list)

Initiation meeting chaired by Paul Salmon

- Future Activites (list)

Paul salmon to lead

4 development workshops planned for 2025

Strengthening bonds with key international organisations where we already have strong bonds: ISO, ILO, WHO

- What stakeholders (groups) are involved, in what roles

- Strengthening bonds with key international organisations will be done specifically in conjunction with the Science, Technology, and Practice Standing Committee (STP), the Development and Promotion Standing Committee (DP), and the Advisory Group on Standardisation (AGS)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by President, STP, DP, and AGS | Influencers |
| Project leader/s | - Development of joint projects | Experts and influencers |
| Experts | - Development of joint projects - Content for joint projects | Experts |

- Benefits to stakeholders

- Joint production of knowledge and promotional material

- Contributing to globally important research and development

- Contributing to international HF/E standards

- Table of activities and resources required

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Development of new AGS guidelines | JES | 20 hours | None yet |
| Appointment of new AGS Chair | Officers | 1 hour + 1 hour meeting with new AGS Chair | None yet |
| Met with ILO | Officers | 3 hours | None yet |
| Development of joint proposal with ILO | STP, relevant TCs | 4 hours | None yet. Anticipated that ILO will provide $20k in financial resources |
| Continuation of joint proposal with WHO | STP, relevant TCs | 0 hours | None yet. |

- Outcomes to date (list)

ISO Joint proposal with TC 283 and TC 159 (Ergonomics) for standards on ergonomic sadety management

3 x meetings with ILO

ILO point proposal developed and submitted to ILO

Preliminary development of expert team for ILO joint proposal

JES to represent IEA at OSH Osaka in July

Evaluation of existing MoUs

- Future Activites (list)

ILO meeting in Geneva on 24 March 2025

WHO meeting in Geneva on 25 March 2025

Follow up renewal of MoUs with Applied Ergonomics Society, Foundation for Professional Ergonomics, INCOSE, ISQUA, ILO, Taylor & Francis, and CNAM.