Update report for Professional Standards and Education

Presentation at 28.3./29.3.2025

Prepared by Verena Nitsch, PSE Chair

The Professional Standards and Education (PS&E) Committee aims to advance global human factors/ergonomics (HFE) by improving education standards, expanding certification access, and engaging the next generation of professionals.

Over the next three years, our focus will center on two key objectives:

- strengthening global HFE education and certification, and

(2) attracting and developing young professionals.

These objectives will be pursued in collaboration with the International Development (ID) Committee to ensure a broad international impact, particularly in developing regions.

Co-chair listing:

- PSE Co-Chairs:

  - Liang Ma (CHN)

  - Rob Becker (UK)

  - Andrew Todd (ZAF)

- Co-Chairs Subcommittee Certification

  - Valerie O‘Keefe (AUS)

  - Stephven Kolose (NZ)

Summary plan for 2024-2027 term:

| Project / initiative | How does this create value-added? | How does this align with IEA strategies policies? | What needs will be met? | Goals to be reached | Milestones (Outline to measure progress) | Current status [to start / in progress / completed] |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Promoting accessible Certification | Strengthens professional standards and recognition of HFE specialists globally. Encourages mutual recognition and standardization. | (4)Identify the Roles of IEA in Promoting Education, Certification and Professional Standards | Standardization of certification processes Greater accessibility to certification Improved professional credibility | In partnership with the IDC, we will expand access to low-cost, regionally tailored certification programs, ensuring that more professionals in resource-constrained regions can attain HFE credentials and grow in their careers. | Collect „best practice“ curricula from different countries/perspectives (China, UK, France, etc.) Divide collected curricula amongst team members and check w.r.t. IEA core competencies Discuss if competencies should be expanded (e.g. w.r.t. practioners‘ requirements, new work trends, UX methods). On-going: Endorsement of Certification Processes | 5 curricula collected Current Certification Endorsement Application: Malaysia Exchange with CREE scheduled Exchange with FEES Exchange with ENETOSH- European Network Education and Training in Occupational Safety and Health |
| 2 Repository educational Tools | Centralized, accessible overview of educational resources for HFE professionals. Improves learning accessibility, promotes HFE research & jobs | (4)Identify the Roles of IEA in Promoting Education, Certification and Professional Standards | Easier access to quality educational tools Better knowledge dissemination Resource sharing amongst societies | A centralized overview of open-access educational materials, including case studies, webinars, and instructional methods. This cost-effective solution will provide faculty and professionals with resources to enhance ergonomics education globally, without requiring significant new course development. | Survey regarding educational resources & mentorship Publish overview with collection of links on website; Annual Update | Survey is finalized First links collected |
| 3 Promoting young members through (virtual) mentorship | Encourages next-generation participation in HFE. Supports career development and knowledge transfer. | (7) Maintain a future focus for HF/E | Attracts young professionals Provides structured international mentorship Fosters career & competence development | A virtual mentorship program will connect students with experienced professionals for career guidance, fostering professional growth through short-term, cost-effective engagements. | Survey regarding educational resources & mentorship Mentorship Program Launch | Survey is finalized |

Project 1: Promoting accessible Certification

For each project described in the Summary Table complete sections 1-7 (if applicable)

- List of Stakeholder groups, and their roles

Specific + by category: System actor / Expert / Decision-Maker / Influencer

[Include commonalities with other IEA EC committees, if applicable.]

| Stakeholder Group | Role within the Project | Role category |
| --- | --- | --- |
| - IEA PSE | - Project oversight - Ensure alignment with core competencies | - Decision-maker |
| - Certifying bodies/course providers | - Apply for endorsement - Provide & access best practice curricula | - Expert |

- List of individual stakeholders, and their roles

Specific + by category: System actors / Experts/ Decision-Makers / Influencers

| Stakeholder | Person’s role within the Project | Role type |
| --- | --- | --- |
| IEA PSE Chair | - Coordinate activities, outreach to certifying bodies & course providers | Influencer, Expert, Decision-maker |
| PSE Co-Chairs | - outreach to certifying bodies & course providers | Expert, decision-maker |
| Subcommittee Co-Chairs | - advise on certification process, prepare suggestions for endorsements | Expert, decision-maker |
| Contact person Certifying bodies/course providers | - provide documentation for certification endorsement - provide best practice curricula | Influencer, Expert |

- Map of relations between stakeholders

| From To | IEA PSE Chair & Co-Chairs | Certifying Bodies & Course Providers |
| --- | --- | --- |
| IEA PSE Chair & Co-Chairs | Project oversight | Collection of best practices, Application for Endorsement |
| Certifying Bodies & Course Providers | Outreach, provide access to curricula |  |

- Benefits to stakeholders

[List – if beyond those listed in Summary plan on page 1]

- Activities and resources required [only include this section in report document, not in presentation]

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Collection of Best Practice Curricula | FEES, CREE, University of Nottingham, University of Derby, Artee, SSA, ACED | 10 | Dropbox |

- Outcomes to date

5 best practice curricula collected

- Future Activites

- Collect further “best practice“ curricula from different countries/perspectives (China, UK, France, etc.)

- Divide collected curricula amongst team members and check w.r.t. IEA core competencies

- Discuss if competencies should be expanded (e.g. w.r.t. practioners‘ requirements, new work trends, UX methods).

- On-going: Endorsement of Certification Processes

Project 2 Repository educational Tools

For each project described in the Summary Table complete sections 1-7 (if applicable)

- List of Stakeholder groups, and their roles

Specific + by category: System actor / Expert / Decision-Maker / Influencer

[Include commonalities with other IEA EC committees, if applicable.]

| Stakeholder Group | Role within the Project | Role category |
| --- | --- | --- |
| - IEA PSE | - Project oversight - Ensure diversity and accessibility of material | - Decision-maker |
| - Federated Societies, Course Providers | - Provide links to & disseminate educational material | - Expert, Influencer |

- List of individual stakeholders, and their roles

Specific + by category: System actors / Experts/ Decision-Makers / Influencers

| Stakeholder | Person’s role within the Project | Role type |
| --- | --- | --- |
| IEA PSE Chair | - Coordinate activities, survey existing material, compile collection, disseminate to societies | Influencer, Expert, Decision-maker |
| PSE Co-Chairs | - outreach to societies & providers to collect links | Expert, decision-maker |
| Contact person Societies /course providers | - provide links to free, accessible educational material, contact & encourage members to contribute | Influencer, Expert |

- Map of relations between stakeholders

| From To | IEA PSE Chair & Co-Chairs | Federated Societies, Course Providers |
| --- | --- | --- |
| IEA PSE Chair & Co-Chairs | Project oversight | provide links to free, accessible educational material, |
| Federated Societies | Outreach, disseminate course material | Encourage society members to contribute |

- Benefits to stakeholders

[List – if beyond those listed in Summary plan on page 1]

- Activities and resources required [only include this section in report document, not in presentation]

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Survey on educational material | IEA Council Members | 1 | Dropbox |

- Outcomes to date

Finalized draft of survey

- Future Activites

- Collect responses from survey

- On-going: Annual update of material overview & check of continued availability

Project 3 Promoting young members through (virtual) mentorship

For each project described in the Summary Table complete sections 1-7 (if applicable)

- List of Stakeholder groups, and their roles

Specific + by category: System actor / Expert / Decision-Maker / Influencer

[Include commonalities with other IEA EC committees, if applicable.]

| Stakeholder Group | Role within the Project | Role category |
| --- | --- | --- |
| - IEA PSE | - Project oversight - Setup & coordinate mentorship programm | Decision-maker |
| - Federated Societies | - Support mentorship program: acquire mentors & mentees - Collect further ideas on promoting young members | Expert, Influencer |

- List of individual stakeholders, and their roles

Specific + by category: System actors / Experts/ Decision-Makers / Influencers

| Stakeholder | Person’s role within the Project | Role type |
| --- | --- | --- |
| IEA PSE Chair | - Coordinate activities, setup & coordinate mentorship programm | Influencer, Expert, Decision-maker |
| PSE Co-Chairs | - outreach to societies, collect ideas on promoting young members, support mentorship program coordination in different regions | Expert, decision-maker |
| IEA Council Members | - take part in survey, acquire mentors & mentees | Influencer, Expert |

- Map of relations between stakeholders

| From To | IEA PSE Chair & Co-Chairs | Federated Societies |
| --- | --- | --- |
| IEA PSE Chair & Co-Chairs | Project oversight | Take part in survey, name interested mentors & mentees |
| Federated Societies | Outreach, coordinate international mentorship programm | Encourage society members to contribute |

- Benefits to stakeholders

[List – if beyond those listed in Summary plan on page 1]

- Activities and resources required [only include this section in report document, not in presentation]

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Survey on mentorship needs& existing programms, & other ideas to promote young members | IEA Council Members | 1 | Dropbox |

- Outcomes to date

Finalized draft of survey

- Future Activites

- Collect responses from survey

- Organizing virtual meet-ups & mentorship program launch