Update report for IEA2027]

Presentation at [28-29 March, Aachen]

Prepared by [Ben Peachey, IEA co-chair]

Introduction paragraph (standing committee purpose, goals, in a few words). This can be from the IEA website or an updated version you propose.

Co-chair listing:

Who is involved, in what roles, why? – see Ambition document

Summary plan for 2024-2027 term:

| Project / initiative | How does this create value-added? | How does this align with IEA strategies policies? | What needs will be met? | Goals to be reached | Milestones (Outline to measure progress) | Current status [to start / in progress / completed] |
| --- | --- | --- | --- | --- | --- | --- |
| 1 IEA 2027 | Brings global HF community together; opportunity to engage partners | Contributes to all 7 strategic polocies | ? | 2,000 attendees; sponsorship targets tbc; | Listed below |  |
|  |  |  |  |  | Ambition document | Complete – approved by CIEHF Council, Andrew Thatcher and Rosemary Seva |
|  |  |  |  |  | Event company selection | Complete – appointed in December 2024 |
|  |  |  |  |  | Company setup and IEA agreements | In progress – due April 2025 |
|  |  |  |  |  | Venue selection/date | Venue chosen; negotiating on available dates |
|  |  |  |  |  | Draft budget | In development; due June 2025 |
|  |  |  |  |  | Sponsorship packages | Not started – due July 2025 |
|  |  |  |  |  | Programme outline and design | Not started – due June 2026 |
|  |  |  |  |  | Paper submissions, ticket and accommodation booking launch | Not started – 12 months before event |
|  |  |  |  |  | Programme launch | Not started – date tbc |
|  |  |  |  |  | Conference delivery | Not started – date tbc |
|  |  |  |  |  | Post-event evaluation | Not started – 1 month after event |
|  |  |  |  |  | Event report to IEA | Not started – tbc after event |

- List of Stakeholder groups, and their roles

Specific + by category: System actor / Expert / Decision-Maker / Influencer

[Include commonalities with other IEA EC committees, if applicable.]

| Stakeholder Group | Role within the Project | Role category |
| --- | --- | --- |
|  | See ambition document |  |

- List of individual stakeholders, and their roles

Specific + by category: System actors / Experts/ Decision-Makers / Influencers

| Stakeholder | Person’s role within the Project | Role type |
| --- | --- | --- |

- Map of relations between stakeholders

| From To | Stakeholder A | Stakeholder B | Stakeholder C | Stakeholder D | Stakeholder E |
| --- | --- | --- | --- | --- | --- |
| Stakeholder A |  |  |  |  |  |
| Stakeholder B |  |  |  |  |  |
| Stakeholder C |  |  |  |  |  |
| Stakeholder D |  |  |  |  |  |
| Stakeholder E |  |  |  |  |  |

- Benefits to stakeholders

[List – if beyond those listed in Summary plan on page 1]

- Activities and resources required [only include this section in report document, not in presentation]

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |

- Outcomes to date

- Future Activites