Update report for the IEA President

Presentation at Nottingham, 25-26 April, 2026

Prepared by Andrew Thatcher, President

The President represents the IEA, chairs the Council and Executive Committee meetings, forms new ad hoc Committees and restructures existing executive committees, appoints Chairs to Committees, and oversees the work of Committees.

Summary plan for 2024-2027 term

| Project / initiative | How does this create value-added? | How does it align with IEA strategies policies | What needs will be met | Goals associated | Milestones (Outline to measure progress) | Current status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Reflecting on the Strategy for the Future of HF/E (Dul et al., 2012) – what has worked, what has not worked, what must still be done | Provide direction for IEA | Contribute to Science, Technology, and Practice Maintain a Future Focus for HF/E | Future focus | Production of paper Revised strategy development | Development Workshops (through 2025) Draft paper produced (early 2026) Panel discussion at EHF2026 on 29 April, 2026 Paper accepted (end 2026) Strategy development (through 2026 and 2027) | Paul Salmon as Project Lead; Project launched 4 March, 2025 |

| 2. Strengthening bonds with key international organisations where we already have strong bonds: ISO, ILO, WHO | Building capacity to support HF/E internationally | Contribute to Science, Technology, and Practice Strengthen Relationships with External Partners | Relationship building | Strengthen international recognition of HF/E | Regular meetings with international organisations. Joint project initiation. | Meet with ILO and WHO in March 2025 in Geneva Plenary meet with ISO in April 2025 AGS Chair, Masaaki Mochimaru appointed 5 March 2025 New MoUs negotiated and signed with ILO, WHO, and FPE. |
| --- | --- | --- | --- | --- | --- | --- |
| 3. Supporting the growth and sustainability of HF/E through developing and supporting the next generation HF/E people | Ensure successive pipeline of researchers, practitioners, and future leaders | Engage stakeholders Contribute to Science, Technology, and Practice | Succession planning | Production of career videos. | Regular ambassadorial visits and presentations | Andrew Todd & Martin Rodriguez to lead (FPE to assist) Ongoing |

1. Reflecting on the Strategy for the Future of HF/E (Dul et al., 2012) – what has worked, what has not worked, what must still be done

- What stakeholders (groups) are involved, in what roles

- This future planning activity will be activated specifically in conjunction with the Science, Technology, and Practice Standing Committee (STP)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by STP and President | Influencer |
| Project leader/s | - Development of analysis and content | Experts and influencers |
| Experts | - Development of paper and strategy workshops | Experts |

- Benefits to stakeholders

- Evaluation of Dul et al. (2012) strategy – successes, failures, progress

- Development of new/refinement of existing strategy based on evaluation

- Table of activities and resources required

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Project initiation on 4 March 2025 | HFESA, ACE, CIEHF, HFES, ESSA, CES, GfA | 20 hours + 10 hours planning | None yet |

- Outcomes to date (list)

Initiation meeting chaired by Paul Salmon

HFE Causal Loop Diagram created

MiroBoard created and active for discussion

First draft circulated for discussion, January 2026

First panel discussion at EHF2026, 29 April 2026

- Future Activities

Paul Salmon to lead (other contributors include Catherine Burns, Mica Endsley, Ayse Gurses, Peter Hancock, Linda Onnasch, Gemma Read, Steve Shorrock, Sarah Sharples, Neville Stanton, Guy Walker, and Mark Young))

Further paper writing and presentations planned for 2026

2. Strengthening bonds with key international organisations where we already have strong bonds, especially ISO, ILO, WHO

- What stakeholders (groups) are involved, in what roles

- Strengthening bonds with key international organisations will be done specifically in conjunction with the Science, Technology, and Practice Standing Committee (STP), The Professional Standards & Education Standing Committee, the Development and Promotion Standing Committee (DP), and the Advisory Group on Standardisation (AGS)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by President, STP, DP, PSE, and AGS | Influencers |
| Project leader/s | - Development of joint projects | Experts and influencers |
| Experts | - Development of joint projects - Content for joint projects | Experts |

- Benefits to stakeholders

- Joint production of knowledge and promotional material

- Contributing to globally important research and development

- Contributing to international HF/E standards

- Table of activities and resources required

| Activity undertaken | Societies/committees involved | Hours dedicated to activity | Resources used |
| --- | --- | --- | --- |
| Development of new AGS guidelines | JES | 20 hours | None yet |
| Appointment of new AGS Chair | Officers | 1 hour + 1 hour meeting with new AGS Chair | None yet |
| ISO TC 159 Plenary meeting | Officers | 2025 8 hours | None yet |
| Met with ILO | Officers | 6 hours | None yet |
| Development of joint proposal with ILO | STP, relevant TCs | 4 hours | ILO will provide $15k in financial resources |
| Development of background document for ILO Convention | Officers, HFES, HFEM, CES, CIEHF, GfA, NES, HFESA | 1.5 hour weekly meeting (20 hours) 3 day meeting in Munich in 2025 (24 hours) 2 day meeting in Beijing in 2025 (16 hours) Writing and reviewing report (100+ hours) | $15k provided by ILO |
| Continuation of Non-State Actor status with WHO | STP, relevant TCs, HFES, HFESS | 4 hours | None yet. |

Outcomes to date

ISO:

ISO Joint proposal with TC 283 (Occupational Safety) and TC 159 (Ergonomics) for standards on ergonomic safety management, developed in conjunction with Safety & Health TC

IEA liaison report for TC 159 Plenary meeting

Two-day TC 159 Plenary meeting (16-17 April 2025, online), Category A liaison status confirmed for IEA

Planning for TC 159 Plenary meeting in London in 2027 in conjunction with IEA2027

ILO:

8 x online meetings with ILO

1 x in-person meeting with ILO (24 March 2025)

ILO/IEA joint proposal developed and submitted to ILO for development of an ILO Convention on Ergonomics

Appointment of expert team for ILO Convention background document. Chair: Carisa Harris, HFES; Wendy MacDonald, HFESA; Chris Kelly, CIEHF; Esa-Pekka Takala (NES), Klaus Bengler (GfA), Shamsul Bhari (HFESM); Chaoyi Zhao (CES); Andrew Thatcher (ESSA)

Weekly meetings of the expert team for ILO Convention background document

In-person meeting of expert team for ILO Convention background document: 14-16 September 2025, Munich and 2-3 November 2025, Beijing. Carisa Harris gave presentation to Council 29 October 2025

WHO:

WHO/IEA guidance document on patient safety using HFE – first draft produced and reviewed by WHO, final version expected 31 March 2026 – Kathleen Mosier (HFES), Michelle Robertson (HFES), Pascal Carayon (HFES), and SQ Yin (HFESS)

WHO/IEA case studies on patient safety using HFE currently being developed for release at end of 2026

IEA Non-State Actor programme of action 2026-2028 accepted by WHO – Shanqing Yin (HFEM), Michelle Robertson (HFES) – further developing guidance on HFE in patient safety

IEA/ICOH/IOHA:

  - OSH World Expo in Osaka, 16-19 July 2025, represented by Masaaki Mochimaru (JES)

  - Joint IEA/IOHA/ICOH statement on gutting of NIOSH in United States

  - IEA to Chair the Human-Centred Workplaces Working Group, OSH World Expo in Riyadh in 2030

Founding declaration of Global Occupational Safety and Health (GOSH), IEA as founding member, 19 July 2025

Founding member of Global Coalition on Informal Workers, IEA as founding member, 25 August 2025

  - Acran Salman Navarro (HFES) – President

  - Maggie Graf (SwissErgo) – Treasurer

  - Clive d’Souza (HFES) – HFES representative

Development of Informal Work Conference, 9-11 November 2026, in Cali hosted by Universidad del Valle

INSTATS

Online platform to replace YouTube for webinars

Secure platform for hosting and storing webinars

Easier platform for potential monetization (allows easy price setting for different categories of users)

Discounted access to other content on the system

OTHERS

Renewal of MoUs with Foundation for Professional Ergonomics (FPE)

  - Ongoing projects involve assistance with recording IEA Fellows and financial assistance to attend IEA2027

Taylor & Francis,

- Future Activities (list)

Consideration of ILO background document to develop into a Convention (ILO, April 2026)

In-person attendance at International Labour Conference (ILC) in June 2026

Ongoing GOSH meetings (once a month)

Evaluation of existing MoUs

Consideration of renewal of MoUs with Applied Ergonomics Society, INCOSE, ISQUA, ILO, and CNAM.

3. Supporting the growth and sustainability of HF/E through developing and supporting the next generation HF/E people

- What stakeholders (groups) are involved, in what roles

- Succession planning will be done in conjunction with the Professional Standards and Education Standing Committee (PSE), the International Development Standing Committee (ID), and the Development and Promotions Standing Committee (DP)

| Stakeholder Group | Stakeholder groups’ role within the Project | Role type |
| --- | --- | --- |
| IEA Executive committee | - Project oversight by PSE, ID, and DP | Influencer |
| Project leader/s | - President | Expert and influencer |

- Benefits to stakeholders

- IEA presence, speak to relevant national stakeholders including society members and especially students

- Outcomes to date

- Signed renewal of Tsinghua Award Collaborative Human Factors and Ergonomics Education and Kingfar Award for Research in Human factors and Ergonomics

- Ambassador visits (in-person)

Shenzhen 2024 (Keynote address at CES conference and handing out awards for student papers).

Zagreb 2024 (Keynote address at CSE conference)

Douliu 2025 (Keynote address at EST conference and handing out awards for student papers)

Mexicali 2025 (Keynote address at SEMAC conference and meet with young and emerging ergonomists)

Aachen 2025 (Keynote address at GfA Spring Congress)

Cali 2025 (seminars at Universidad del Valle for PhD programme in HFE for South America)

Makhanda 2025 (HKE 80th Anniversary – two presentations at 80th anniversary of department)

Singapore 2025 (seminars at DSO and SUSS)

Beijing 2025 (Keynote address at CES conference and handing out awards for student papers)

Fortaleza 2025 (Keynote address at ABERGO/ULAERGO conference)

- Ambassador visits (online)

ABERGO 2024 (Welcome address for ABERGO conference)

ErgoWork 2024 (Welcome address for ErgoWork, Romania, Conference)

Subraya 2024 (Keynote address at PEI conference)

SustainX 2025 (Keynote address at HESP student award conference)

AdEA 2025 (Welcome address for AdEA Congress)

ESSA 2025 (Welcome address for ESSA conference)

HFES Puget Sound (Welcome address for Puget Sound meeting)

HFES Nordic 2025 (presentation to Nordic countries)

SASOM 2025 (presentation at seminar on informal work)

Maria Cano University 2025 (presentation at the International Congress of Ergonomics in Colombia, SCE)

BAuA 2025 (presentation at the Climate Change Meets Occupational Safety and Health symposium)

Costa Rica 2026 (presentation to Department of Labour and Social Security and UTN)

Technology for Co-working on Health and Active conference 2025 (Keynote address for Bulgarian Ergonomics Society)

- Future Activities

Ambassador visit (in-person): EHF 2026 (panel contributor at CIEHF conference, 27-29 April 2026 Nottingham)

Ambassador visit (in-person): Nagoya 2026 (Keynote address at JES conference, 23-24 May 2026 and presentation at Nagoya City University, 22 May 2026)

Ambassador visit (in-person): Humanizing Work and Work Environment 2026 (Keynote address at HWWE 2026, hosted at UPES, Dehradun, 9–11 December 2026