## Slide 1
Professional Standards &
Education Committee
Progress report on four projects
IEA Council Meeting · November 2026 · Florianópolis, Brazil
Verena Nitsch, Chair PSE

## Slide 2
PROFESSIONAL STANDARDS & EDUCATION
Our mission and team
PSE Committee · IEA Council Meeting 2026 2
We advance global HFE by improving education standards, expanding certification access and engaging the next generation of professionals.
1
Strengthen global HFE education and certification
2
Attract and develop young professionals
In collaboration with the International Development Committee, with a focus on developing regions.
PSE CO-CHAIRS
Liang Ma CHN
Rob Becker UK
Andrew Todd ZAF
Daniel Braatz BRA
Farzan Sasangohar USA
NEW
CERTIFICATION SUBCOMMITTEE
Stephven Kolose NZ
Valerie O'Keefe AUS
Rose Figueroa USA
NEW
Thank you to Yining Ye and Denizsu Topkaya for their supporting work.

## Slide 3
OVERVIEW
Four projects at a glance
PSE Committee · IEA Council Meeting 2026 3
A
International Mentoring Network
Connect existing society-led mentoring programmes
Survey sent to all Federated Societies
IN PROGRESS
B
Shared HFE Educational Resources
A governed platform for open learning resources
Interactive prototype ready for review
IN PROGRESS
C
HFE Curricula & Programme Database
Best-practice curricula and a searchable programme overview
303 HFE programmes in the new database
IN PROGRESS
D
Certification (Re-)Endorsement
Guide certification bodies through (re-)endorsement
CREE & ESSA scored by three assessors
IN PROGRESS

## Slide 4
PROJECT A · INTERNATIONAL MENTORING NETWORK
Connecting mentoring programmes across societies
PSE Committee · IEA Council Meeting 2026 4
Goal Make society-led mentoring visible, identify collaboration opportunities and let IEA facilitate connections
Discussions with HFES & IFPE
Completed
Survey developed & sent to all societies
Completed
Data collection & follow-up
In progress
Inventory of mentoring activities
Next
Recommendations for IEA coordination
Next
WHAT WE LEARNED
Mentoring takes very different forms across societies: formal committees (e.g. HFES), mentor matching, student mentoring, conference programming and leadership mentoring.
PLANNED OUTCOMES
Inventory of mentorship activities
Good practices and shareable resources
Unmet needs & map of collaboration interest
Recommendations: cross-promotion, joint virtual activities, mentor referral
Lead: Farzan Sasangohar (HFES)

## Slide 5
PROJECT B · SHARED HFE EDUCATIONAL RESOURCES
A governed platform for open HFE learning resources
PSE Committee · IEA Council Meeting 2026 5
Lead: Liang Ma · with Yining Ye
BENCHMARK OF FIVE PLATFORMS
Coursera
edX
FutureLearn
OpenLearn
OER Commons
DESIGN PRIORITIES
Easy to find
Search, topic entry points and course cards
Provenance & licence
Licence and third-party material as mandatory fields
Clear review roles
Professional and compliance review separated
Complete records
Versions, review outcomes and access status kept
TWO-STAGE REVIEW
Submission
Creator selects licence, confirms rights, flags third-party material
▼
1 · HFE content review
Professional relevance, classification, completeness
▼
2 · IEA final review
Copyright, privacy, conditions for public release
▼
Publication
Version control, link checks, complaint handling

## Slide 6
PROJECT B · SHARED HFE EDUCATIONAL RESOURCES
Interaction prototype of the IEA platform
PSE Committee · IEA Council Meeting 2026 6
01
Trust by design
Every published resource carries a traceable professional and legal review record.
02
Built on the research
Translates platform structure, user roles and key workflows into an interactive interface.
03
Next step
Review and discussion of the prototype with PSE and EC; decision on implementation and hosting.
Figures shown in the prototype are placeholder demo data.

## Slide 7
PROJECT C · HFE CURRICULA & PROGRAMME DATABASE
From the Global Map to a searchable programme database
PSE Committee · IEA Council Meeting 2026 7
BEFORE · GOOGLE GLOBAL MAP
Double work: data in Google Drive and Google Earth
Shared Google account caused login conflicts
Multi-step updates and coordination meetings
NOW · CENTRAL EXCEL DATABASE
One central file – no shared account needed
Two layers: filter tab and main database tab
New programmes added as a simple new row
303
HFE programmes in the database to date
records migrated from the previous IEA database
BEST-PRACTICE HFE CURRICULA
A collection of HFE curricula with an overview of covered subjects has been compiled to guide those who wish to establish new courses. The overview is shared with Council members – further curricula are welcome.

## Slide 8
PROJECT C · HFE CURRICULA & PROGRAMME DATABASE
The new database in practice
PSE Committee · IEA Council Meeting 2026 8
Sheet 1 · Filter
Search tool: filter programmes by region, country, city and university
Sheet 2 · Database
Single source: programme, degree, language, duration, contacts and links
NEXT STEPS
Share with initial users for feedback on usability and search
Regional contacts verify, add and update programmes
Add reporting features (pivot tables, formatting)

## Slide 9
PROJECT D · CERTIFICATION (RE-)ENDORSEMENT
Building a shared knowledge base on certification
PSE Committee · IEA Council Meeting 2026 9
Certification Subcommittee: S. Kolose, V. O'Keefe, R. Figueroa
History of the IEA Certification Endorsement System
S. Kolose · January 2026 · foundational resource for the Subcommittee
1961
IEA mandate: science into practice
2000
Quality Assurance Committee; endorsement criteria
2001
IEA Core Competencies
2010s
Alignment with ISO/IEC 17024
2020s
Hybrid exam + portfolio models
CHALLENGES IDENTIFIED
Language barriers in applications and assessment
Loss of institutional memory between committee cycles
Shrinking pool of volunteer assessors
Overview and comparison of certification criteria
Circulated to certification bodies for review
9
certification bodies compared
7
dimensions per system
Education · work experience · supervised practice · portfolio · examination · referees · special notes
KEY OBSERVATIONS
All systems rely on work experience and work samples / portfolios
Only 2 of 9 use a written examination (BCPE, JES)
Endorsement so far focuses on process rather than content

## Slide 10
PROJECT D · CERTIFICATION (RE-)ENDORSEMENT
A rubric to standardise re-endorsement scoring
PSE Committee · IEA Council Meeting 2026 10
Rubric IEA-CSC-RUB-01
35 CRITERIA IN 7 WEIGHTED DOMAINS
Core competency alignment
25%
8
Professional behaviour & ethics
25%
4
Assessment methodology & rigour
20%
6
Governance & independence
15%
5
Continuing professional development
7.5%
4
Certification lifecycle management
5%
4
Transparency & documentation
2.5%
4
■ critical domain ■ non-critical · right column: number of criteria
0–3 SCALE PER CRITERION
3
Fully
2
Substantially
1
Partial
0
Gap
MULTI-REVIEWER PROCESS
Lead reviewer
scores + justification
Co-reviewer
scores independently
Divergences
flagged for discussion
Result
recommendation by fixed rules
Optional third reviewer · final decision remains with the Subcommittee
DECISION THRESHOLDS
Weighted score
Critical Reds
Total Reds
Full
≥ 85%
0
≤ 1
Conditional
≥ 40%
≤ 4
≤ 6
Non-endorsement
< 40%
≥ 5
≥ 7
Non-endorsement if weighted score < 40% or either Red trigger is reached.
Tested on the CREE and ESSA applications, scored independently by three assessors.

## Slide 11
PROJECT D · CERTIFICATION (RE-)ENDORSEMENT
Re-endorsement schedule
PSE Committee · IEA Council Meeting 2026 11
Certification body | First endorsement | Last re-endorsement | Next due | Status
Argentina (ADEA) | 2024 | – | 2030 | Not due
Australia (HFESA) | prob. 2007 | 2021 | 2027 | Not due
Brazil (ABERGO) | 2018 | – | 2024 | Re-endorsement required
Canada (CCCPE) | 2020 | – | 2026 | Expected Jan 2027
Europe (CREE) | before 2009 | 2020 | 2026 | Submitted – scored
Japan (JES) | 2006 | 2019 | 2025 | Re-endorsement required
Malaysia (HFEM) | 2025 | – | 2031 | Not due
New Zealand (HFESNZ) | 2007 | 2021 | 2027 | Not due
South Africa (ESSA) | before 2022 | – | 2023–2027 | Submitted – scored
USA (BCPE) | before 2009 | 2020 | 2026 | Due
Mexico has not applied, but maintains long-standing communication with IEA about its established system. Source: PSE re-endorsement overview, Sept 2026.

## Slide 12
HOW COUNCIL MEMBERS CAN HELP
Your contribution makes these projects work
PSE Committee · IEA Council Meeting 2026 12
Complete the mentorship survey
Share your society's mentoring activities and interest in collaboration.
Send HFE curricula
Add curricula from your country to the best-practice collection.
Verify programme data
Check and complete the HFE programmes listed for your region.
Volunteer
We need active contributors, e.g. as assessors for re-endorsements.
Mentorship survey
IEA Mentorship Activities and Coordination Survey – scan to respond

## Slide 13
Thank you
Questions and discussion
Verena Nitsch
Chair, Professional Standards & Education Committee
iea.cc